## Plan
Project Objective | Create a webpage that allows users to read, write stories, rate and review other users’ stories.
Roles | Features
Users | - Write and publish stories. - Upload cover photos for stories. - Rate and review stories. - Filter stories by date, rating, views, and optionally by genre.
Admins | - Delete inappropriate reviews. - Delete story posts. - Manage user accounts (optional).
Requirements and Project Estimations
Task | Description | Estimated Hours
Explore Different Websites | Research similar platforms for feature inspiration and best practices | 1.5
Design Layout | Create UI prototype | 1.5
Code Frontend | Develop core frontend components using React | 10
Design and develop Database | Design and setup local database | 5
Backend Integration Plan | Outline how frontend will communicate with backend APIs | 2.5
Buffer | To deal with bugs & unexpected changes | 5
Backend Coding | Implement backend functionalities using Go | 7
Connect Backend and Frontend | Integrate frontend with backend APIs | 7
39.5

## Progress
Daily Task Progress Report
Date | Task | Hours | Worklog
2024-11-14 | Define Project Objective | - | Done
2024-11-14 | Define roles and their features | - | Done
2024-11-14 | Define requiremnets and estimation | - | Done
2024-11-15 | Researched 3 similar platforms for inspiration | 1.5 | Done
2024-11-15 | Created UI prototype in Figma | 1.5 | Done
2024-11-15 | Explore the Frontend tech to be used | 1 | Done
2024-11-16 | Design Homepage | 4
2024-11-16 | Explore the database options | 1