## Plan
Project Objective | Create a webpage that allows users to read, write stories, rate and review other users’ stories.
Roles | Features
Users | - Write and publish stories. - Upload cover photos for stories. - Rate and review stories. - Filter stories by date, rating, views, and optionally by genre.
Admins | - Delete inappropriate reviews. - Delete story posts. - Manage user accounts (optional).
Requirements and Project Estimations
Task | Description | Estimated Hours
Explore Different Websites | Research similar platforms for feature inspiration and best practices | 1.5
Design Layout | Create UI prototype | 1.5
Code Frontend | Develop core frontend components using React | 10
Design and develop Database | Design and setup local database | 5
Backend Integration Plan | Outline how frontend will communicate with backend APIs | 2.5
Buffer | To deal with bugs & unexpected changes | 5
Backend Coding | Implement backend functionalities using Go | 7
Connect Backend and Frontend | Integrate frontend with backend APIs | 7
39.5